## Issue Log
Mobile App Issue Tracker
How to use: register projects on the 'Projects' sheet, then pick a Project for every issue and fill the cream cells. ID and Days Open fill in automatically. Row 6 is an example – overwrite it.
Filter the Project column to see one project's issues, or use the 'Dashboard' sheet to pick a project (or All Projects) and see its summary.
ID | Project | Title | Description | Module / Screen | Platform | Type | Severity | Priority | Status | Steps to Reproduce | Expected Result | Actual Result | App Version / Build | Device / OS | Reported By | Assigned To | Date Reported | Target Date | Date Resolved | Days Open | Fixed in Version | Notes / Link
APP-001 | My Mobile App | App crashes on login with Google Sign-In | App closes immediately after selecting a Google account on the login screen. | Login | Android | Crash | Critical | P1 | Open | 1. Open app 2. Tap 'Sign in with Google' 3. Choose an account | User lands on Home screen | App force-closes (NullPointerException) | 1.2.0 (45) | Pixel 6 / Android 14 | QA Team | Dev A | 2026-10-09 | 2026-10-16 |  | 3 |  | Logcat attached in drive folder
Formulas:
Days Open = IF([Date Reported]="","",IF([Date Resolved]<>"",[Date Resolved]-[Date Reported],TODAY()-[Date Reported]))

## Dashboard
Issue Dashboard
Pick a project (or All Projects) in the yellow cell. Everything on the left updates; the table on the right always shows every project.
Project: | All Projects | *
Key Numbers | Count |  |  | All Projects Summary | Total | Open | Crit/High Open | Overdue | Resolved %
Total issues | 1 |  |  | My Mobile App | 1 | 1 | 1 | 0 | 0%
Open (not Resolved / Closed / Won't Fix) | 1
Critical & High still open | 1
Overdue (past Target Date, unresolved) | 0
Reopened issues | 0
Average days to resolve | 0
Resolution rate | 0%
By Status | Count | By Severity | Count
New | 0 | Critical | 1
Open | 1 | High | 0
In Progress | 0 | Medium | 0
In Review | 0 | Low | 0
Ready for QA | 0
Resolved | 0
Closed | 0 |  |  | Total (all projects) | 1 | 1 | 1 | 0
Reopened | 0
Won't Fix | 0
By Platform | Count | By Type | Count
Android | 1 | Bug | 0
iOS | 0 | Crash | 1
Both | 0 | UI/UX | 0
Backend/API | 0 | Performance | 0
Web/Admin | 0 | Security | 0
|  | Data/Sync | 0
|  | Feature Request | 0
|  | Other | 0
By Priority | Count
P1 | 1
P2 | 0
P3 | 0
P4 | 0

## Projects
Projects
Add each project here (one per row, up to 15). Its name then appears in the Issue Log and Dashboard dropdowns, and its Code becomes the issue ID prefix (e.g. APP-001).
Keep Project Names unique and keep Codes short (2–5 letters). Row 6 is an example – overwrite it.
Project Name | Code | Lead / Owner | Start Date | Notes
My Mobile App | APP | Project Manager | 2026-08-13 | Example project

## Lists
Platform | Type | Severity | Priority | Status | Dashboard selector (auto) | Edit the option lists to change dropdowns. Column G is automatic – don't edit.
Android | Bug | Critical | P1 | New | All Projects
iOS | Crash | High | P2 | Open | My Mobile App
Both | UI/UX | Medium | P3 | In Progress
Backend/API | Performance | Low | P4 | In Review
Web/Admin | Security |  |  | Ready for QA
| Data/Sync |  |  | Resolved
| Feature Request |  |  | Closed
| Other |  |  | Reopened
Won't Fix